## Sheet1
SD CUSTOM HOMES
SWORN CONSTRUCTION STATEMENT
PROJECT/CLIENT: 1908 South Lane
RESIDENCE
|  |  | CONTRACT + CHANGE ORDERS |  |  |  | COSTS | DOWN PAYMENTS + DRAWS
Item | TYPE OF | COST | TOTAL | Actual Bids | Lot Purchase | CHANGE | ACTUAL | DOWN | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | DRAW | BALANCE
# | IMPROVEMENT | CODES | CONTRACT |  |  | ORDER | BIDS/COSTS | PAYMENT | 1 | 2 | 3 | 4 | 6 | 5 | 6 | 7 | 8 | TO
| FURNISHED |  | PRICE | [5 empty] | 2026-01-14 | 2026-03-25 | 2026-05-04 | 2026-06-25 |  | 2026-08-19 |  |  |  | COMPLETE
1 | Plans | 1.01 | 14500 | 6370 |  |  | 8178.47 | 0 | 14456.33 | 525 | [7 empty] | -481.33
2 | Interior Design- Elevation Drawings | 1.02 | 5000 |  |  |  | 0 | 0 | [9 empty] | 5000
3 | Permit | 1.03 | 16300 | 5500 |  |  | 13109.64 | 0 | 16213.64 | [8 empty] | 86.36
4 | Engineering | 1.04 |  |  |  |  | 1180 | 0 |  | 595 | [7 empty] | -595
5 | Plot plans/Staking | 2.01 | 7800 | 1500 |  |  | 2261.25 | 0 | 7800 | [8 empty] | 0
6 | Tree Care/Removal | 2.02 | 10000 | 2000 |  |  | 0 | 0 | 9906 | [8 empty] | 94
7 | Dirt Haul/Removal | 2.03 | 5000 |  |  |  | 5000 | 0 |  | 2180 | 3935 | [6 empty] | -1115
8 | Excavation | 2.04 | 28000 | 7000 |  |  | 25298.32 | 0 | 27418 |  | 375 | [6 empty] | 207
9 | Utility connections/ Assesment | 2.05 | 25000 |  |  |  |  | 0 | 4265.25 |  | 1000 | 4159.3 | [5 empty] | 15575.45
10 | Foundation | 3.01 | 41000 | 22963 |  |  | 47768.08 | 0 | 40906.2 | [8 empty] | 93.8
11 | Waterproofing | 3.02 | 8000 | 4152 |  |  | 9500 | 0 | 7384.07 | [8 empty] | 615.93
12 | Concrete/flatwork | 3.03 | 31000 | 10000 |  |  | 22000 | 0 |  | 15568.97 | 9258.09 | 2236.23 |  | 2236.23 |  |  |  | 1700.48
13 | Equipment Rental | 3.04 | 0 |  |  |  | 0 | 0 | [9 empty] | 0
14 | Rough lumber | 4.01 | 80000 | 46226.32 |  |  | 110000 | 0 | 54000 | 14828.33 | 2940.65 |  |  | 7588.14 |  |  |  | 642.88
14A | Trusses | 4.01A | 42000 |  |  |  |  | 0 | 16403.57 | 27091.54 | [7 empty] | -1495.11
15 | Rough carpentry | 4.02 | 64000 | 22115.75 |  |  | 56719.5 | 0 | 25000 | 20000 | 14226 | [6 empty] | 4774
16 | Roofing material/shingles | 4.03 | 18000 | 6900 |  |  | 20000 | 0 |  | 16892.18 | [7 empty] | 1107.82
16A | Roof - Metal | 4.03A | 6000 |  |  |  |  | 0 | [5 empty] | 5100 |  |  |  | 900
16B | Roofing labor | 4.03B | 12000 |  |  |  |  | 0 |  | 7150 | [7 empty] | 4850
18 | Insulation | 4.05 | 23000 | 8343.84 |  |  | 14000 | 0 |  |  | 29022.31 | [6 empty] | -6022.31
19 | Windows | 4.06 | 98000 | 17856.14 |  |  | 57971.69 | 0 |  | 102638.31 | [7 empty] | -4638.31
19A | Window Install | 4.06A | 8500 |  |  |  |  | 0 |  |  | 8496.36 | [6 empty] | 3.64
20 | Exterior doors | 4.07 | 25000 | 4985 |  |  | 15000 | 0 |  |  | 720.67 |  |  | 20068.35 |  |  |  | 4210.98
21 | Exterior Lock Set/Door Hardware | 4.08 | 1000 |  |  |  | 1000 | 0 | [9 empty] | 1000
22 | Garage doors | 4.09 | 11000 | 4300 |  |  | 16000 | 0 | [5 empty] | 14021.15 |  |  |  | -3021.15
23 | Gutters/sheet metal | 4.1 | 4500 |  |  |  | 2400 | 0 | [9 empty] | 4500
24 | Siding MATERIAL | 4.11 | 25000 | 28000 |  |  | 57000 | 0 |  |  | 24258.18 | 2925.37 |  | 302.28 |  |  |  | -2485.83
25 | Siding Labor | 4.12 | 25000 |  |  |  |  | 0 |  |  | 18000 | [6 empty] | 7000
25A | Stucco Material & Labor | 4.12A | 13000 |  |  |  |  | 0 | [5 empty] | 4400 |  |  |  | 8600
26 | Plumbing MATERIAL | 4.13 | 25000 | 6500 |  |  | 13000 | 0 |  | 3817.75 |  | 1262.83 |  | 2301.9 |  |  |  | 17617.52
27 | Plumbing LABOR | 4.14 | 30000 | 14655 |  |  | 26000 | 0 |  | 15000 | [7 empty] | 15000
28 | HVAC | 4.15 | 46000 | 21788 |  |  | 40000 | 0 |  | 9200 | 14540 |  |  | 6000 |  |  |  | 16260
29 | Electrical labor | 4.16 | 40000 | 16380 |  |  | 28000 | 0 |  | 25000 |  |  |  | 2992.72 |  |  |  | 12007.28
30 | Brick/stone materials | 4.17 | 46000 | 6000 |  |  | 8000 | 0 | [5 empty] | 42303.92 |  |  |  | 3696.08
31 | Fireplace | 4.18 | 18000 | 4000 |  |  | 12000 | 0 |  |  | 8546.77 |  |  | 9453.23 |  |  |  | 0
32 | Drywall | 4.19 | 46000 | 17840 |  |  | 35000 | 0 |  |  |  | 45633 | [5 empty] | 367
33 | Finish trim MATERIAL | 5.01 | 30000 | 15670 |  |  | 34000 | 0 |  | 1385.01 |  | 28614.99 |  | 946 |  |  |  | -946
34 | Finish trim LABOR | 5.02 | 20000 | 10670 |  |  | 20000 | 0 |  |  |  | 20000 | [5 empty] | 0
35 | Misc. Carpentry + Materials | 5.03 | 12000 |  |  |  | 2000 | 0 |  | 892.15 | 491.54 | 2503.51 |  | 8112.8 |  |  |  | -9.0949e-13
36 | Interior Door Hardware | 5.04 | 5500 |  |  |  | 2500 | 0 | [5 empty] | 503.2 |  |  |  | 4996.8
37 | Wood Beams | 5.05 | 4000 |  |  |  | 4000 | 0 | [9 empty] | 4000
38 | Cabinetry | 5.06 | 120000 |  |  |  | 85000 | 0 | 7500 | 47480 | 15117.5 | 49902.5 | [5 empty] | 0
39 | Cabinet Hardware | 5.07 | 500 |  |  |  | 500 | 0 | [5 empty] | 1404.42 |  |  |  | -904.42
40 | Counter Tops | 5.08 | 40000 |  |  |  | 31000 | 0 | [5 empty] | 22591.76 |  |  |  | 17408.24
41 | Paint (Interior) | 5.09 | 75000 |  |  |  | 35000 | 0 | [5 empty] | 2306.42 |  |  |  | 72693.58
42 | Paint (Exterior) | 5.1 | 15000 |  |  |  | 2500 | 0 | [9 empty] | 15000
43 | Mirrors | 6.01 | 4000 | 2500 |  |  | 2500 | 0 | [9 empty] | 4000
44 | Shower Doors+ Wine Closet | 6.02 | 4500 |  |  |  | 4500 | 0 | [9 empty] | 4500
45 | Bath Accessories | 6.03 | 1500 |  |  |  | 500 | 0 | [9 empty] | 1500
46 | Ceramic Tile | 6.04 | 50000 | 18532.5 |  |  | 40000 | 0 |  |  | 16419.83 | 27007.31 |  | 20699.81 |  |  |  | -14126.95
47 | Flooring - Wood | 6.05 | 40000 | 12500 |  |  | 30000 | 0 |  | 23543 |  | 14215 | [5 empty] | 2242
48 | Flooring - Carpet | 6.06 | 18000 | 7500 |  |  | 9800 | 0 | [9 empty] | 18000
49 | Flooring - LVT | 6.07 | 2800 |  |  |  | 5600 | 0 | [9 empty] | 2800
50 | Light fixtures | 6.08 | 15000 | 3500 |  |  | 9000 | 0 | [9 empty] | 15000
51 | Appliances | 6.09 | 63000 | 8500 |  |  | 42000 | 0 | [9 empty] | 63000
52 | Shelving | 6.1 | 25000 | 3000 |  |  | 9000 | 0 | [9 empty] | 25000
53 | Wallpaper | 6.11 | 0 |  |  |  | 0 | 0 | [9 empty] | 0
54 | Low Voltage | 6.12 | 10000 |  |  |  | 0 | 0 |  |  | 9580.77 | [6 empty] | 419.23
55 | Garage Coating | 6.13 | 5500 |  |  |  | 0 | 0 | [9 empty] | 5500
56 | Driveway (asphalt/concrete) | 7.01 | 12000 |  |  |  | 12000 | 0 | [9 empty] | 12000
57 | Deck | 7.02 | 0 |  |  |  | 0 | 0 | [9 empty] | 0
58 | Phantom Screens | 7.03 | 0 |  |  |  | 0 | 0 | [9 empty] | 0
59 | Golf Simulator | 7.04 | 0 |  |  |  | 0 | 0 | [9 empty] | 0
60 | EZ Screens | 7.05 | 6500 |  |  |  | 6500 | 0 | [9 empty] | 6500
61 | Porch Materials | 7.06 | 15000 |  |  |  | 30000 | 0 | [5 empty] | 6300.42 |  |  |  | 8699.58
62 | Sod/irrigation/landscaping | 7.07 | 0 | 7500 |  |  | 25000 | 0 | [9 empty] | 0
63 | Demo | 7.08 | 0 | 48312 |  |  | 6500 | 0 | [9 empty] | 0
64 | Utilities | 8.01 | 5000 |  |  |  | 5000 | 0 | 56.25 | 82.22 | 51.35 | 337.57 |  | 436.51 |  |  |  | 4036.1
65 | Debris Removal | 8.02 | 4000 |  |  |  | 3500 | 0 |  | 1695 |  | 2485 |  | 1330.17 |  |  |  | -1510.17
66 | Site Sanitation ($150/mo) | 8.03 | 2000 |  |  |  | 2000 | 0 | 448.92 | 587.36 | 175.11 | 350.51 |  | 346.76 |  |  |  | 91.34
67 | Site Maintenance/Cleaning | 8.04 | 5000 |  |  |  | 1500 | 0 | [9 empty] | 5000
68 | Paint Touch Ups | 9.01 | 6170 |  |  |  | 0 | 0 | [9 empty] | 6170
69 | Final + Window Clean | 9.02 | 4500 |  |  |  | 4500 | 0 | [9 empty] | 4500
70 | Punch List | 9.03 | 12000 |  |  |  | 5000 | 0 | [9 empty] | 12000
71 | Contingency | 9.04 | 170899.68 |  |  |  | 21812.4 | 0 | 13420.28 | 6637.12 | 12903.03 | 47089.36 |  | 11792.12 |  |  |  | 79057.77
72 | BR Insurance | 10.01 | 4200 |  |  |  | 4150.65 | 0 | 3762 | [8 empty] | 438
73 | Pre-Construction Planning/PM/Permitting | 10.02 | 5000 |  |  |  | 5000 | 0 | 5000 | [8 empty] | 0
74 | Project Management | 10.03 | 55000 |  |  |  | 30000 | 0 | 6875 | 8000 | 8000 | 8000 |  | 10000 |  |  |  | 14125
75 | Builder Profit + Overhead | 10.04 | 560000 |  |  |  | 460000 | 250500 | 38750 | 45000 | 45000 | 45000 |  | 50000 |  |  |  | 85750
76 | Warranty | 10.05 | 8000 |  |  |  | 8000 | 0 | [9 empty] | 8000
77 | Lot Purchase | 11.01 | 0 |  | 640000 |  | 650000 | 0 | [9 empty] | 0
78 | Real Estate Commission | 11.02 | 169830.32 |  |  |  | 0 | 0 | 169830.32 | [8 empty] | 0
590996.28
| TOTAL |  | 2505000 | 423559.55 |  | 0 | 2296250 | 250500 | 469395.83 | 395788.94 | 243058.16 | 301722.48 | 0 | 253538.31 | 0 |  | 0 | 590996.28
STATUS
| Original Contract |  |  |  |  | 2505000 | Total BUDGET
| CO 1 |  |  |  |  | 640000 | Summary | Signed By | ____________________
| CO 2 | [7 empty] | Sean Doyle, Owner
| Updated Contract |  |  |  |  | 3145000
| Change Orders #1 |  |  |  |  | 0
Cost
P + O
| Change Orders #2 |  |  |  |  | 0
Cost
P + O
2081440.45