## Sheet1
SD CUSTOM HOMES
SWORN CONSTRUCTION STATEMENT
PROJECT/CLIENT: 1908 South Lane - KAREN HOFFMANN
1908 SOUTH LANE, MENDOTA HEIGHTS, MN 55120
|  |  | CONTRACT + CHANGE ORDERS |  |  | DOWN PAYMENTS + DRAWS
Item # | Type of improvement furnished | Cost code | Total contract price | Change order 1 | Change order 2 | Down payment | Draw 3 (current) | Previous draws | Cumulative draws | Balance to complete
1 | Plans | 1.01 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 14500
2 | Interior Design - Elevation Drawings | 1.02 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
3 | Permit | 1.03 | 16300 | 0 | 0 | 0 | 0 | 0 | 0 | 16300
4 | Engineering | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Plot plans/Staking | 2.01 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 7800
6 | Tree Care/Removal | 2.02 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
7 | Dirt Haul/Removal | 2.03 | 5000 | 0 | 0 | 0 | 3935 | 0 | 3935 | 1065
8 | Excavation | 2.04 | 28000 | 0 | 0 | 0 | 375 | 0 | 375 | 27625
9 | Utility connections/ Assesment | 2.05 | 25000 | 0 | 0 | 0 | 1000 | 0 | 1000 | 24000
10 | Foundation | 3.01 | 41000 | 0 | 0 | 0 | 0 | 0 | 0 | 41000
11 | Waterproofing | 3.02 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
12 | Concrete/flatwork | 3.03 | 31000 | 0 | 0 | 0 | 9258.09 | 0 | 9258.09 | 21741.91
13 | Equipment Rental | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Rough lumber | 4.01 | 80000 | 0 | 0 | 0 | 2940.65 | 0 | 2940.65 | 77059.35
14A | Trusses | 4.01A | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 42000
15 | Rough carpentry | 4.02 | 64000 | 0 | 0 | 0 | 14226 | 0 | 14226 | 49774
16 | Roofing material/shingles | 4.03 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
16A | Roofing - Metal | 4.03A | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000
16B | Roofing labor | 4.03B | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
17 | Roofing labor | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Insulation | 4.05 | 23000 | 0 | 0 | 0 | 29022.31 | 0 | 29022.31 | -6022.31
19 | Windows | 4.06 | 98000 | 0 | 0 | 0 | 0 | 0 | 0 | 98000
19A | Window Installation | 4.06A | 8500 | 0 | 0 | 0 | 8496.36 | 0 | 8496.36 | 3.64
20 | Exterior doors | 4.07 | 25000 | 0 | 0 | 0 | 720.67 | 0 | 720.67 | 24279.33
21 | Exterior Lock Set/Door Hardware | 4.08 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
22 | Garage doors | 4.09 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 11000
23 | Gutters/sheet metal | 4.10 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
24 | Siding MATERIAL | 4.11 | 25000 | 0 | 0 | 0 | 24258.18 | 0 | 24258.18 | 741.82
25 | Siding Misc | 4.12 | 25000 | 0 | 0 | 0 | 18000 | 0 | 18000 | 7000
25A | Stucco Material & Labor | 4.12A | 13000 | 0 | 0 | 0 | 0 | 0 | 0 | 13000
26 | Plumbing MATERIAL | 4.13 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
27 | Plumbing LABOR | 4.14 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
28 | HVAC | 4.15 | 46000 | 0 | 0 | 0 | 14540 | 0 | 14540 | 31460
29 | Electrical labor | 4.16 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
30 | Brick/stone materials | 4.17 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
31 | Fireplace | 4.18 | 18000 | 0 | 0 | 0 | 8546.77 | 0 | 8546.77 | 9453.23
32 | Drywall | 4.19 | 46000 | 0 | 0 | 0 | 0 | 0 | 0 | 46000
33 | Finish trim MATERIAL | 5.01 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 30000
34 | Finish trim LABOR | 5.02 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 20000
35 | Misc. Carpentry + Materials | 5.03 | 12000 | 0 | 0 | 0 | 491.54 | 0 | 491.54 | 11508.46
36 | Interior Door Hardware | 5.04 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
37 | Wood Beams | 5.05 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
38 | Cabinetry | 5.06 | 120000 | 0 | 0 | 0 | 15117.5 | 0 | 15117.5 | 104882.5
38A | Cabinetry Installation | 5.06A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Cabinet Hardware | 5.07 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 500
40 | Countertops | 5.08 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
41 | Paint (Interior) | 5.09 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
42 | Paint (Exterior) | 5.10 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
43 | Mirrors | 6.01 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
44 | Shower Doors+ Wine Closet | 6.02 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
45 | Bath Accessories | 6.03 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
46 | Ceramic Tile | 6.04 | 50000 | 0 | 0 | 0 | 16419.83 | 0 | 16419.83 | 33580.17
47 | Flooring - Wood | 6.05 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000
48 | Flooring - Carpet | 6.06 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000
49 | Flooring - LVT | 6.07 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 2800
50 | Light fixtures | 6.08 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
51 | Appliances | 6.09 | 63000 | 0 | 0 | 0 | 0 | 0 | 0 | 63000
52 | Closets & Shelving | 6.10 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000
53 | Wallpaper | 6.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Low Voltage | 6.12 | 10000 | 0 | 0 | 0 | 9580.77 | 0 | 9580.77 | 419.23
55 | Garage Coating | 6.13 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 5500
56 | Driveway (asphalt/concrete) | 7.01 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
57 | Deck | 7.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | Phantom Screens | 7.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | Golf Simulator/Sport Court | 7.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | EZ Screens | 7.05 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 6500
61 | Porch Materials | 7.06 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
62 | Sod/irrigation/landscaping | 7.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | Demo | 7.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | Utilities | 8.01 | 5000 | 0 | 0 | 0 | 51.35 | 0 | 51.35 | 4948.65
65 | Debris Removal | 8.02 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
66 | Site Sanitation ($200/mo) | 8.03 | 2000 | 0 | 0 | 0 | 175.11 | 0 | 175.11 | 1824.89
67 | Site Maintenance/Cleaning | 8.04 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
68 | Paint Touch Ups | 9.01 | 6170 | 0 | 0 | 0 | 0 | 0 | 0 | 6170
69 | Final + Window Clean | 9.02 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500
70 | Punch List | 9.03 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000
71 | Contingency | 9.04 | 170899.68 | 0 | 0 | 0 | 12903.03 | 0 | 12903.03 | 157996.65
72 | BR Insurance | 10.01 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 4200
73 | Pre-Construction Planning/PM/Permitting | 10.02 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000
74 | Project Management | 10.03 | 55000 | 0 | 0 | 0 | 8000 | 0 | 8000 | 47000
75 | Builder Profit + Overhead | 10.04 | 560000 | 0 | 0 | 250500 | 45000 | 0 | 45000 | 264500
76 | Warranty | 10.05 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000
77 | Lot Purchase | 11.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Real Estate Commission | 11.02 | 169830.32 | 0 | 0 | 0 | 0 | 0 | 0 | 169830.32
79 | CHANGE ORDER #1 | 11.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | CHANGE ORDER #2 | 11.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | CHANGE ORDER #3 | 11.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL |  | 2505000 | 0 | 0 | 250500 | 243058.16 | 0 | 243058.16 | 2011441.84
Prior draw records not yet supplied: 1, 2. Previous/cumulative amounts reflect recorded draws only.
Balance to complete = total contract price + change order 1 + change order 2 - down payment - cumulative draws.
Final draw package